TRANSPORT EDUCATION TRAINING AUTHORITY (TETA)

TETA-IPPCMS

Detailed Sample Learner Delivery & Monitoring Report

Illustrative management report for Learnership Support Projects

| Report Parameter | Illustrative Detail |
| --- | --- |
| Reporting Period | September 2026 |
| Project ID | TETA-LSP-2026-014 |
| Project | Gauteng Transport Sector Learnership Programme |
| Programme Type | Learnership Support |
| Training Provider | ABC Training Academy (illustrative) |
| Project Manager | TETA Project Manager |
| M&E Officer | TETA Monitoring Officer |
| Contract Period | 1 April 2026 - 31 March 2027 |
| Contract Value | R18,500,000 |
| Overall Project Status | RED - Management Intervention Required |

Purpose: To provide an integrated view of learner delivery, provider performance, monitoring results, evidence completeness, corrective actions and financial delivery alignment.

# A. Executive Delivery Summary

| KPI | Contract / Target | Actual | Variance | % Achievement | Status |
| --- | --- | --- | --- | --- | --- |
| Contracted Learners | 500 | 500 | - | 100% | Green |
| Learners Registered | 500 | 462 | (38) | 92.4% | Amber |
| Learners Commenced | 500 | 448 | (52) | 89.6% | Amber |
| Active Learners | 475 | 421 | (54) | 88.6% | Amber |
| Learners Due for Completion | 350 | 350 | - | - | - |
| Learners Completed | 350 | 281 | (69) | 80.3% | Red |
| Learners Withdrawn | <=15 | 26 | +11 | - | Red |
| Learner Evidence Complete | 100% | 89% | (11%) | 89% | Amber |
| Monitoring Visits Planned | 4 | 4 | - | - | - |
| Monitoring Visits Completed | 4 | 3 | (1) | 75% | Amber |
| Findings Raised | - | 12 | - | - | - |
| Findings Closed | 12 | 5 | (7) | 41.7% | Red |
| Corrective Actions Overdue | 0 | 3 | +3 | - | Red |

Management assessment: Learner recruitment and commencement are below the contracted target. Completion performance is materially behind plan, withdrawals exceed the illustrative tolerance, and monitoring has identified unresolved findings and overdue corrective actions. Management intervention is required.

# B. Learner Delivery by Cohort

| Cohort | Planned | Registered | Commenced | Active | Completed | Withdrawn | Completion % | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cohort 1 | 100 | 100 | 98 | 92 | 88 | 6 | 88.0% | Green |
| Cohort 2 | 100 | 98 | 96 | 90 | 82 | 8 | 82.0% | Amber |
| Cohort 3 | 100 | 95 | 92 | 88 | 74 | 7 | 77.9% | Amber |
| Cohort 4 | 100 | 91 | 86 | 79 | 37 | 5 | 40.7% | Red |
| Cohort 5 | 100 | 78 | 76 | 72 | - | - | Not yet due | Amber |
| Total | 500 | 462 | 448 | 421 | 281 | 26 | 80.3%* | Red |

* Completion percentage compares 281 completions with the 350 learners due for completion, not all 500 contracted learners.

# C. Detailed Learner Status Register

| Learner Ref. | Cohort | Registration | Start Date | Current Status | Progress | Evidence | Exception |
| --- | --- | --- | --- | --- | --- | --- | --- |
| LRN-000181 | 1 | Complete | 15 Apr | Completed | 100% | Complete | None |
| LRN-000182 | 1 | Complete | 15 Apr | Completed | 100% | Complete | None |
| LRN-000183 | 1 | Complete | 15 Apr | Active | 85% | Complete | Assessment outstanding |
| LRN-000184 | 1 | Complete | 15 Apr | Active | 80% | Incomplete | Attendance evidence missing |
| LRN-000185 | 2 | Complete | 10 May | Withdrawn | 42% | Complete | Withdrawal |
| LRN-000186 | 2 | Complete | 10 May | Active | 73% | Complete | Behind programme |
| LRN-000187 | 3 | Complete | 01 Jun | Suspended | 55% | Incomplete | Provider follow-up required |
| LRN-000188 | 4 | Complete | 01 Jul | Active | 46% | Complete | Behind schedule |

Note: CEO and Board reporting should normally use aggregated learner information. Individual learner details should be restricted to authorised operational users in accordance with configured access and privacy controls.

# D. Learner Exceptions

| Exception Category | No. Learners | Impact | Responsible Party | Required Action | Due Date | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Registration outstanding | 38 | Target shortfall | Provider | Complete registrations | 05 Oct | Amber |
| Did not commence | 14 | Delivery shortfall | Provider | Confirm/recover learners | 05 Oct | Red |
| Behind programme schedule | 47 | Completion risk | Provider | Implement catch-up plan | 15 Oct | Red |
| Withdrawals | 26 | Reduced completions | Provider/TETA PM | Analyse causes/replacement options | 10 Oct | Red |
| Missing evidence | 51 | Verification/payment risk | Provider | Upload outstanding evidence | 10 Oct | Amber |
| Assessment outstanding | 34 | Completion delay | Provider | Complete assessments | 20 Oct | Amber |
| Potential duplicate records | 3 | Data/funding risk | TETA | Investigate duplicate flags | 03 Oct | Red |

# E. Training Delivery Performance

| Deliverable | Planned | Actual | Variance | Evidence | Status |
| --- | --- | --- | --- | --- | --- |
| Learner recruitment | 500 | 462 | (38) | Registration records | Amber |
| Induction completed | 500 | 448 | (52) | Induction registers | Amber |
| Training modules delivered | 24 | 22 | (2) | Training records | Amber |
| Workplace placements | 450 | 407 | (43) | Placement evidence | Red |
| Assessments completed | 350 | 316 | (34) | Assessment records | Amber |
| Learners completed | 350 | 281 | (69) | Completion evidence | Red |
| Monthly provider reports | 6 | 6 | - | Reports uploaded | Green |

## Delivery Trend

| Month | Planned Active Learners | Actual Active | Planned Completions | Actual Completions |
| --- | --- | --- | --- | --- |
| May | 100 | 98 | - | - |
| June | 200 | 188 | 50 | 46 |
| July | 300 | 274 | 120 | 105 |
| August | 400 | 367 | 230 | 194 |
| September | 475 | 421 | 350 | 281 |

# F. Monitoring Visit Programme

| Visit | Planned Date | Actual Date | Monitoring Type | Scope | Findings | Status |
| --- | --- | --- | --- | --- | --- | --- |
| MV-01 | 15 May | 15 May | Site Visit | Mobilisation & enrolment | 2 | Completed |
| MV-02 | 15 Jul | 17 Jul | Site Visit | Training & attendance | 4 | Completed |
| MV-03 | 15 Sep | 18 Sep | Site Visit | Learners, workplace & evidence | 6 | Completed |
| MV-04 | 25 Sep | - | Follow-up | Corrective actions | - | Red - Overdue |

# G. Monitoring Findings Register

| Finding | Description | Severity | Date Raised | Owner | Due Date | Status |
| --- | --- | --- | --- | --- | --- | --- |
| F-001 | Learner registration documentation incomplete | Medium | 15 May | Provider | 31 May | Closed |
| F-002 | Attendance records incomplete | High | 17 Jul | Provider | 31 Jul | Red - Overdue |
| F-003 | Workplace placement evidence outstanding | High | 17 Jul | Provider | 05 Aug | Red - Overdue |
| F-004 | Learner files missing assessment evidence | Medium | 18 Sep | Provider | 05 Oct | Amber - Open |
| F-005 | Learner progress behind approved schedule | High | 18 Sep | Provider | 30 Sep | Red - Overdue |
| F-006 | Provider monthly report inconsistencies | Medium | 18 Sep | Provider | 10 Oct | Amber - Open |
| F-007 | Potential duplicate learner records | High | 18 Sep | TETA PM | 03 Oct | Amber - Open |

# H. Corrective Action Tracking

| Corrective Action | Related Finding | Responsible Person | Due Date | Evidence Required | Current Position | Escalation |
| --- | --- | --- | --- | --- | --- | --- |
| Reconstruct attendance records | F-002 | Provider PM | 31 Jul | Verified registers | Outstanding | EXCO escalation |
| Complete workplace evidence | F-003 | Provider PM | 05 Aug | Placement agreements | 70% received | Contract Manager |
| Implement learner catch-up plan | F-005 | Provider Academic Lead | 30 Sep | Recovery plan | Not accepted | Executive intervention |
| Complete learner evidence | F-004 | Provider Administrator | 05 Oct | Learner files | In progress | Project Manager |
| Investigate duplicate learners | F-007 | TETA PM | 03 Oct | Verification report | In progress | M&E Manager |

# I. Evidence Completeness

| Evidence Category | Required | Received | Verified | Outstanding | Completeness |
| --- | --- | --- | --- | --- | --- |
| Learner registration records | 500 | 462 | 459 | 38 | 92.4% |
| Attendance records | 448 | 421 | 397 | 27 | 94.0% |
| Workplace placement evidence | 450 | 407 | 390 | 43 | 90.4% |
| Assessment evidence | 350 | 316 | 298 | 34 | 90.3% |
| Completion evidence | 350 | 281 | 281 | 69 | 80.3% |
| Provider monthly reports | 6 | 6 | 6 | 0 | 100% |

# J. Financial Delivery Alignment

| Financial Measure | Amount | Delivery Measure | Result |
| --- | --- | --- | --- |
| Approved Contract | R18.50m | Contracted Learners | 500 |
| Budget to Date | R11.20m | Expected Completions | 350 |
| Actual Expenditure | R9.80m | Actual Completions | 281 |
| Commitments | R3.40m | Active Learners | 421 |
| Remaining Budget | R5.30m | Completion Achievement | 80.3% |
| Forecast Final Cost | R17.60m | Forecast Learners Completed | 455 |
| Forecast Underspend | R0.90m | Forecast Completion Rate | 91.0% |

Key management question: Does the level of expenditure correspond with verified learner delivery?

# K. Payment Milestone Control

| Payment | Value | Required Deliverable | Delivery Status | Evidence | Certification | Payment |
| --- | --- | --- | --- | --- | --- | --- |
| Milestone 1 | R3.70m | Mobilisation/enrolment | Completed | Verified | Approved | Paid |
| Milestone 2 | R3.70m | Training commencement | Completed | Verified | Approved | Paid |
| Milestone 3 | R3.70m | 50% programme progress | Partial | Some outstanding | Conditional | Part paid |
| Milestone 4 | R3.70m | Learner completion | Behind plan | Incomplete | Not approved | Held |
| Final | R3.70m | Close-out/outcomes | Not due | Not due | Not due | Not due |

# L. Provider Performance Scorecard

| Performance Area | Weight* | Score | Weighted Result | Status |
| --- | --- | --- | --- | --- |
| Learner Recruitment | 15% | 92% | 13.8% | Amber |
| Training Delivery | 20% | 88% | 17.6% | Amber |
| Learner Completion | 25% | 80% | 20.0% | Red |
| Evidence Quality | 15% | 89% | 13.4% | Amber |
| Monitoring Compliance | 10% | 75% | 7.5% | Red |
| Corrective Action Closure | 10% | 42% | 4.2% | Red |
| Reporting | 5% | 100% | 5.0% | Green |
| Overall Provider Score | 100% | - | 81.5% | Amber |

* Weights and scoring thresholds are illustrative and should be approved by TETA before system configuration.

# M. Risks and Management Actions

| Risk / Issue | Impact | Rating | Action | Owner | Due Date |
| --- | --- | --- | --- | --- | --- |
| Completion shortfall | APP target may not be achieved | High | Recovery programme | Provider/TETA PM | 15 Oct |
| High learner withdrawals | Reduced project outcomes | High | Root-cause analysis | Provider | 10 Oct |
| Missing evidence | Payment/performance verification risk | Medium | Evidence remediation | Provider | 10 Oct |
| Delayed monitoring | Weak oversight | Medium | Complete follow-up visit | M&E | 07 Oct |
| Outstanding corrective actions | Continued non-compliance | High | Executive escalation | Contract Manager | Immediate |

# N. Management Decisions Required

1. Provider Recovery Plan: Require a formal recovery plan for the 69 learner completion shortfall.

2. Payment Control: Hold or condition the affected milestone payment until required deliverables and evidence are accepted in accordance with applicable contract and approval rules.

3. Corrective Actions: Escalate the three overdue high-priority corrective actions.

4. Monitoring: Complete the outstanding follow-up monitoring visit.

5. Learner Evidence: Require remediation of incomplete learner evidence before the next performance certification.

6. Forecast: Reforecast learner completions and project expenditure based on the recovery plan.

# O. Recommended TETA-IPPCMS Screen / Report Structure

The system should present this report as a summary dashboard with drill-down tabs rather than as one static report. Recommended tabs:

| Tab | Purpose |
| --- | --- |
| Executive Summary | Headline delivery, monitoring, financial and exception indicators. |
| Learner Delivery | Targets, cohort performance, completion and withdrawal trends. |
| Learner Register | Authorised learner-level status and exceptions. |
| Provider Delivery | Deliverables, milestones and provider performance. |
| Monitoring Visits | Planned/completed visits and monitoring evidence. |
| Findings | Finding severity, ownership, ageing and status. |
| Corrective Actions | Action owners, due dates, evidence and escalation. |
| Evidence | Evidence completeness and verification. |
| Financial Performance | Budget, commitments, expenditure and forecast. |
| Payments | Payment milestones linked to accepted delivery. |
| Risks | Project/provider risks and mitigation. |
| Management Decisions | Decisions, owners and follow-up actions. |

# Report Design Notes

All figures in this sample are illustrative and should not be interpreted as actual TETA performance.

Final KPI definitions, tolerances, RAG thresholds, provider scorecard weights and escalation periods should be validated and approved by TETA.

The report should support drill-down from programme to project, provider, learner cohort, authorised learner record, evidence and audit history.

Learner-level personal information should be protected through role-based access, privacy controls and appropriate aggregation for executive reporting.